Timeline for YANK project including reporting to Soroptimists

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | J | J | A | S | O | N | D | J | F |
| Capacity Assessment | **X** | **X** | **X** |  |  |  |  |  |  |
| Development of the training curriculum for the Government officials  | **X** | **X** |  |  |  |  |  |  |  |
| Capacity strengthening for YANK |  | **X** |  |  |  |  |  |  |  |
| Government officials’ workshop (during 16th June - International Day of the African Child) |  |  | **X** |  |  |  |  |  |  |
| Development of KSW tools for training (drawn from the needs assessment) |  |  | **X** | **X** |  |  |  |  |  |
| Follow ups and monitoring through physical visits, calls and online meetings |  |  | **X** | **X** | **X** | **X** | **X** | **X** | **X** |
| Develop a Youth Ambassador Programme and Launch |  |  |  | **X** | **X** |  |  |  |  |
| International Conference on FGM in Arusha |  |  |  |  | **X** |  |  |  |  |
| 5-days KSW with young people (during youth Week) |  |  |  |  | **X** |  |  |  |  |
| Reporting (photos, narrative describing what activities have taken place and financial including what the grant was spent on). The final report will also include feedback from participants.  |  |  |  |  | **X** |  |  |  | **X** |